## 8349(Offers) - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Trips | Suspend TRIP_ROOT_TASK | Ensure no ongoing run | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Update the warehouse of the trip jobs to 4XL warehouse | Scale up existing warehouse or updating new warehouse in job table? | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Increase the task timeout out to 4 Hours | For trip recalculation task | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Take backup of trip tables using CLONE_TABLE_PROC proc |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Collect all extra SKs in temp table using Adhoc proc (app. Count 154885084) |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST
Production | Trips | Check TRIP_MASTER_ID count for recalculation | Check if the cleanup needs to be performed in chunks | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Run Adhoc proc | Based on the previous step, adhoc scripts needs to be executed ( in chunks if count is huge ) a) Soft delete the extra SKs b) Insert the trip_master_id into trip_recalc_queue | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Execute ON-DEMAND TRIP Tasks | Run the On-Demand tasks from Trip_recalculation_proc to Trip_summary_wrapper_proc | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Validation | Run the Validation queries to confirm no more extra SKs exists | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Revert back the warehouse of the trip jobs to L Warehouse |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Resume TRIP_ROOT_TASK |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Require 2XL role and 4XL upgrade

## 8592(Ratings) - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Trips | Suspend TRIP_ROOT_TASK | Ensure no ongoing run | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Update the warehouse of the trip jobs to 4XL warehouse | Scale up existing warehouse or updating new warehouse in job table? | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Increase the task timeout out to 4 Hours | For trip recalculation task | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Take backup of trip tables using CLONE_TABLE_PROC proc |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Collect all extra SKs in temp table using Adhoc proc (app. Count 1750394951) |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST
Production | Trips | Check TRIP_MASTER_ID count for recalculation | Check if the cleanup needs to be performed in chunks | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Run Adhoc proc | Based on the previous step, adhoc scripts needs to be executed ( in chunks if count is huge ) a) Soft delete the extra SKs b) Insert the trip_master_id into trip_recalc_queue | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Execute ON-DEMAND TRIP Tasks | Run the On-Demand tasks from Trip_recalculation_proc to Trip_summary_wrapper_proc | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Validation | Run the Validation queries to confirm no more extra SKs exists | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Revert back the warehouse of the trip jobs to L Warehouse |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -
Production | Trips | Resume TRIP_ROOT_TASK |  | 01/09/2024 10:00 AM IST | 01/09/2024 10:00 AM IST | Divya/Surya | -

## UAT Stats
8349 - Offers | Warehouse = 2XL
Count of Extra SKs | 154874263
Count of TRIP_MASTER_ID | 47201302
Range of TRIP_MASTER_ID | Number of TRIP_MASTER_ID recalculated | Procedure execution time(TRIP_RECALCULATION_PROC) | Remaining steps of TRIP
<=10000000 | 286250668 | 1 Hour | 1 Hour
10000001 to 23000000 | 435863545 | 1.5 Hour | 1 Hour
23000001 to 36000000 | 457958895 | 2 Hour | 1 Hour
>=36000001 | 317490876 | 1.5 Hour | 1 Hour
8592 - Ratings | Warehouse = 2XL
Count of Extra SKs | 1751968118
Count of TRIP_MASTER_ID | 139569723
Range of TRIP_MASTER_ID | Number of TRIP_MASTER_ID recalculated | Procedure execution time(TRIP_RECALCULATION_PROC) | Remaining steps of TRIP
<=20000000 | 497089790 | 3 Hours | 1 Hour
20000001 AND 40000000 | 492946917 | 3 Hours | 1 Hour
40000001 AND 60000000 | 463014566 | 2.5 Hours | 1 Hour
60000001 AND 80000000 | 496591188 | 1.5 Hours | 1 Hour
80000001 AND 95000000 | 439262908 | 1.5 Hours | 1 Hour
95000001 AND 107500000 | 371596278 | 1 Hour | 1 Hour
107500001 AND 117500000 | 421084032 | 1.5 Hours | 1 Hour
117500001 AND 127500000 | 323757451 | 45 Min | 1 Hour
>=127500001 | 453132182 | 1 Hour | 1 Hour