## Inventory
JIRA# | JIRA | Object Schema | Object | Object Type
8844 | Digital Play 888 source - Incremental Defect - Found during Prod Restore Validation | DAAS_COMMON | trip_digital_play_proc | Procedure
|  | DAAS_TEMP | daily_activity_summary_digital_play_temp_dtf | Table

## 8844 - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Digital Play | Suspend Trip root task |  | 12/19/2023 10:00 AM IST | 12/19/2023 10:01 AM IST | Divya |  | Done
Production | Digital Play | Code Check-in & Deploy procedures & table through Jenkins | trip_digital_play_proc daily_activity_summary_digital_play_temp_dtf | 12/19/2023 10:01 AM IST | 12/19/2023 10:10 AM IST | Divya | - | Done
Production | Digital Play | Validate if the proc is deployed |  | 12/19/2023 10:10 AM IST | 12/19/2023 10:15 AM IST | Divya | - | Done
Production | Digital Play | Capture discrepancy GUEST_UNIQUE_ID & REPORT_DT into temp table | Using adhoc proc | 12/19/2023 10:15 AM IST | 12/19/2023 10:25 AM IST | Divya | - | Done
Production | Digital Play | Replay the captured records in DIGITAL_TRANSACTIONS_FACT | CALL DAAS_COMMON.DATA_REPLAY_PROC | 12/19/2023 10:25 AM IST | 12/19/2023 10:35 AM IST | Divya | - | Done
Production | Digital Play | Execute Trip Root task/trip_summary manually to process the trips |  | 12/19/2023 10:35 AM IST | 12/19/2023 11:00 AM IST | Divya | - | Done
Production | Digital Play | Validate if there is no more discrepancy |  | 12/19/2023 11:00 AM IST | 12/19/2023 11:10 AM IST | Divya | - | Done
Production | Digital Play | Resume Trip root task |  | 12/19/2023 11:10 AM IST | 12/19/2023 11:15 AM IST | Divya | - | Done
Production | Digital Play | Monitor Trip jobs and ensure it complete successfully for 3 to 4 runs |  | 12/19/2023 11:15 AM IST | 12/19/2023 11:20 AM IST | Divya | - | Done