## Inventory
JIRA# | JIRA | Object Schema | Object | Object Type
8396 | Handle Deletes from Offers that has current_status = ‘N’ (Offers Purge Proc) | DAAS_COMMON | pdb_offer_ledger_fact_purge_history_load_proc | Procedure

## 8396 - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Offers | Suspend Trip root task & RAW2CORE_PDB_OFFER_LEDGER_FACT_TASK |  | 12/19/2023 10:00 AM IST | 12/19/2023 10:01 AM IST | Divya |  | Done
Production | Offers | Code Check-in & Deploy procedures through Jenkins | pdb_offer_ledger_fact_purge_history_load_proc | 12/19/2023 10:01 AM IST | 12/19/2023 10:10 AM IST | Divya | - | Done
Production | Offers | Validate if the proc is deployed |  | 12/19/2023 10:10 AM IST | 12/19/2023 10:15 AM IST | Divya | - | Done
Production | Offers | Capture the active SKs into temp table | For the scenario: DELETE_IND = Y, CURRENT_STATUS_IND = N and OFFER_STATUS_CD IN (R,X) | 12/19/2023 10:15 AM IST | 12/19/2023 10:25 AM IST | Divya | - | Done
Production | Offers | Replay the captured SKs from OFFER_LEDGER_FACT_HISTORY | Using Data_Replay Procedure | 12/19/2023 10:25 AM IST | 12/19/2023 10:35 AM IST | Divya | - | Done
Production | Offers | Execute Trip Root task manually to process the trips |  | 12/19/2023 10:35 AM IST | 12/19/2023 11:00 AM IST | Divya | - | Done
Production | Offers | Validate if the records are soft deleted in Trip_Detail | For the scenario: DELETE_IND = Y, CURRENT_STATUS_IND = N and OFFER_STATUS_CD IN (R,X) | 12/19/2023 11:00 AM IST | 12/19/2023 11:10 AM IST | Divya | - | Done
Production | Offers | Resume Trip root task & RAW2CORE_PDB_OFFER_LEDGER_FACT_TASK |  | 12/19/2023 11:10 AM IST | 12/19/2023 11:15 AM IST | Divya | - | Done
Production | Offers | Monitor Trip jobs and ensure it complete successfully for 3 to 4 runs |  | 12/19/2023 11:15 AM IST | 12/19/2023 11:20 AM IST | Divya | - | Done

## Validations
BEFORE FIX:
AFTER FIX: