## Inventory
JIRA# | JIRA | Object Schema | Object | Object Type
DAASS-8844 | Digital Play - Incremental Defect - Found during Prod Restore Validation | DAAS_COMMON | trip_digital_play_proc | Procedure
|  | DAAS_TEMP | daily_activity_summary_digital_play_temp_dtf | table
DAASS-8693 | Business_Start_Dt is greater than Business_End_Dt in Trip_Detail for the active records | DAAS_COMMON | trip_hotel_domain_pipeline_proc | Procedure

## 8693 - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Trips | Suspend TRIP_ROOT_TASK | Ensure no on-going run | 01/24/2024 11:15 AM IST | 01/24/2024 11:20 AM IST | Divya/Surya | - | Done
Production | Trips | Code Check-in & Deploy procedure | trip_hotel_domain_pipeline_proc | 01/24/2024 11:20 AM IST | 01/24/2024 11:25 AM IST | Divya/Surya | - | Done
Production | Trips | Identify the issue records | 31 issue recs as on 01/22/2024 | 01/24/2024 11:25 AM IST | 01/24/2024 11:30 AM IST | Divya/Surya | - | Done
Production | Trips | Call Replay proc to replay issue records from HOTEL_GUEST_RESERVATIONS_FACT |  | 01/24/2024 11:30 AM IST | 01/24/2024 11:35 AM IST | Divya/Surya | - | Done
Production | Trips | Execute TRIP_ROOT_TASK |  | 01/24/2024 11:35 AM IST | 01/24/2024 12:05 PM IST | Divya/Surya | - | Done
Production | Trips | Validate after Trip_Summary Wrapper completion |  | 01/24/2024 12:05 PM IST | 01/24/2024 12:15 PM IST | Divya/Surya | - | Done
Production | Trips | Resume TRIP_ROOT_TASK |  | 01/24/2024 12:15 PM IST | 01/24/2024 12:20 PM IST | Divya/Surya |  | Done

## 8844 - Deployment Plan
Task Type | Feature | Activity | Details | Start Time | End Time | Task Owner | Dependency | Status | Remarks
Production | Trips | Suspend TRIP_ROOT_TASK | Ensure no on-going run | 01/24/2024 10:00 AM IST | 01/24/2024 10:05 AM IST | Divya/Surya | - | Done
Production | Trips | Code Check-in & Deploy trip_digital_play_proc, temp table and Adhoc proc to fix the issue | trip_digital_play_proc daily_activity_summary_digital_play_temp_dtf | 01/24/2024 10:05 AM IST | 01/24/2024 10:20 AM IST | Divya/Surya | - | Done
Production | Trips | Run the Adhoc proc to collect discrepancy records in temp table and replay records from DIGITAL_TRANSACTIONS_FACT | ~1300 recs | 01/24/2024 10:20 AM IST | 01/24/2024 10:40 AM IST | Divya/Surya | - | Done
Production | Trips | Replay trip detail to populate stream | Taken care in 8693 | 01/24/2024 10:40 AM IST | 01/24/2024 10:45 AM IST | Divya/Surya | - | Done
Production | Trips | Execute Trip_Summary_OnDemand task to fix the trips Daily_Activity_Summary |  | 01/24/2024 10:45 AM IST | 01/24/2024 11:10 AM IST | Divya/Surya | - | Done
Production | Trips | Validate the txns after Trip_Summary Wrapper completion |  | 01/24/2024 11:10 AM IST | 01/09/2024 11:15 AM IST | Divya/Surya | - | Done
Production | Trips | Resume TRIP_ROOT_TASK |  | 01/24/2024 11:15 AM IST | 01/09/2024 11:20 AM IST | Divya/Surya | - | Done

## Scripts
8844 - Scripts
Fix Steps
https://github.caesars.com/Data-as-a-Service/DAAS_REPO/blob/UAT/sql/adhoc/ddl/procedures/trip_digital_replay_adhoc_proc.sql
https://github.caesars.com/Data-as-a-Service/DAAS_REPO/blob/UAT/sql/common/daas_common/ddl/procedure/core/trip_digital_play_proc.sql
https://github.caesars.com/Data-as-a-Service/DAAS_REPO/blob/UAT/sql/temp/daas_temp/ddl/table/daily_activity_summary_digital_play_temp_dtf.sql
8693 - Scripts
Fix Steps
https://github.caesars.com/Data-as-a-Service/DAAS_REPO/blob/UAT/sql/common/daas_common/ddl/procedure/core/trip_hotel_domain_pipeline_proc.sql

## Validations
DAASS-8844 Digital Play - Incremental Defect - Found during Prod Restore Validation
Before Fix:
After Fix:
Reason for discrepancy records: As part of '0' metric handling(DAAS-8395), we're deleting records from temp table which are having '0' metrics. Here the scenario is non-zero metrics records in fact are later updated to '0' metrics, which is not getting reflected in DAILY_ACTIVITY_SUMMARY as we're deleting records from temp table. Need code fix for this scenario. The records which are affected by 8844 issue got fixed.
DAASS-8395 Business_Start_Dt is greater than Business_End_Dt in Trip_Detail for the active records
Before:
After: